## Product Backlog
ID | Theme | As a/an | I want to… | so that… | Notes | Priority | Sprint # | Status
1 | Simulator | Player | I want to acess the game in Correct URL and log in to the game Using given Username | I can log in to the game |  | 1 | 1 | Completed
2 | Simulator | Player | As a player I want the play this game connect with others | Then the Game getting complex and can improve the knowledge |  | 1 |  | Completed
3 | Game | Player | As a player If select multiple players | Then other 3 members can join to the game If Is not Connect enough Members to start the game then Computer Plays full filing other members positions. | This is a AI Part | 2 | 1 | Completed
4 | Simulator | Player | See variation between the prices of shares in the market. | Share prices do not always change at the same rate/have the same price. | This is the stock value model | 1 | 1 | Completed
5 | Game | Player | be able to buy shares | they can make money | This needs refinement | 1 | 1 | Completed
6 | Game | Player | be able to see the current price of shares | they can decide what to buy/sell |  | 2 | 1 | Completed
7 | Game | Player | As a Player, initial value should be R.S.1000 and player can buy shares if they have enough money for buy those shares. | they can’t buy shares without enough money | should display following notifications *Error message or notification If player try to buy shares without Enough money *Success message or notification If player buy shares with Enough money | 1 | 1 | Completed
8 | Simulator | Player | when bought shares the Total amount should be decrease From the shares amount. | so that I know my current amount | Function *Total amount=previous amount-Shares price | 1 | 1 | Completed
9 | Game | Player | I want to see my current stocks and others current stocks ,transaction history | easy to get decisions which player can buy/sell | This is Broker component | 3 | 1 | Completed
10 | Game | Player | be able to sell shares | they can make money |  | 1 | 1 | Completed
11 | Simulator | Player | when I sold the shares my current balance should be increase | so that I know my current amount | Function *Total amount=previous amount+Sold share prices | 1 | 1 | Completed
12 | Simulator | Player | when I sold the shares my current balance should be increase | so that I know my current amount | Function *Total amount=previous amount+Sold share prices | 2 | 1 | Completed
13 | Simiulator | Player | All the stocks will be associated with a sector. Ex:-Finance,Technolog,Consumer service, Manufacturing | so that I can play the game with Different sectors | At lease 4 sectors and and 3 sectors should be in the game | 1 | 1 | Completed
14 | Simulator | Player | game should have BOOMS,BUSTS,TAKE OVERS,SACANDALS events. | so that I can get experience in events happening in the stock market world | *Events can have significant effect on the price of stock *Events can apply either sector or a stock *events applied limited period of time | 2 | 1 | Completed
15 | Simulator | Player | Play a game made up of fixed-duration turns | I have only a limited time to decide what to buy and sell | This is an essential property of the game. | 1 | 1 | Completed
16 | Game | Player | Play a game which is modelled with discrete time system | I have limited time to play | To make the game challengable and not avoid player from getting bored. | 2 | 2 | Completed
17 | Game | Player | Play the game with fixed number of turns | I have limited fixed number of turns | To play the game with free mind | 1 | 2 | Completed
18 | Simulator | Player | Should be able to buy/sell shares within the fixed amount of time(10 mins) | Make money as fast as I can to win the game | Encouraging players to make money | 2 | 2 | Completed
19 | Simulator | Player | Want to see the market prices goes up/ down after buying shares | can decide whether to buy/sell in the next round | This is the stock value model | 2 | 2 | Completed
20 | Simulator | Player | Want to see the market prices goes up/ down after selling shares | can decide whether to buy/sell in the next round | This is the stock value model | 2 | 2 | Completed
21 | Game | Player | Player should be able to buy shares at any time | Other players can make money |  | 1 | 2 | Completed
22 | Game | Player | Player should be able to sell shares at any time | Player can make money |  | 1 | 2 | Completed
23 | Game | Player | See the random market component | Player can decide what to buy and sell | This is the stock value model | 1 | 2 | Completed
24 | Game | Player | See the sector trend market component | Player can decide what to buy and sell | This is the stock value model | 1 | 2 | Completed
25 | Game | Player | See the general trend market component | Player can decide what to buy and sell | This is the stock value model | 1 | 2 | Completed
26 | Game | Player | See the event compnent | Player can decide what to buy and sell | This is the stock value model | 1 | 2 | Completed
27 | Simulator | Player | See the negative scores are interpretend to 0 | Make it easy to get decisions |  | 2 | 2 | Completed
28 | Simulator | Player | Want to see the value increasing probability is 0.25 | Player can sell shares | This is the stock value model | 1 | 2 | Completed
29 | Simulator | Player | Want to see the value decreasing probability is 0.25 | Palyer can buy shares | This is the stock value model | 1 | 2 | Completed
30 | Simulator | Player | Want to see the value remains at 0.5 | Player can buy/Sell shares at this time | This is the stock value model | 1 | 2 | Completed
31 | Game | Player | Able to see unique trend is created for each sector | Players could easily identify each sector | To make the game unique | 1 | 2 | Completed
32 | Simulator | Player | One event should be generated per turn | Avoids players from getting confused | To make the game more unique | 1 | 2 | Completed
33 | Simulator | Player | CLOCK: If joined to the game any of these modes Player should display current turn of the game | I know how far into the game I am | Function: now() – returns the current turn | 1 | 3 | Completed
34 | [7 empty] | Completed
34 | Game | Player | BANK: financial transactions related to the purchase / sale of stocks | easy to get decisions can buy/sell,I know account balances and transaction history,Deposit: Increasing balance | This is Bank component.Transaction = turn,type,stock,quantity,price.Transactn type: deposit(turn,name,sender,amount) AND Withdrawal | 2 | 3 | Completed
35 | Game | Player | Players accounts,Player name to use identify for each player's account. Cannot duplicate account | Unique identifier | CreateAccount(turn,name), Account balance is initialized Rs.1000. Exception handling(Account name already exit) | 1 | 3 | Completed
36 | Game | Player | Broker: be able to buy/sell stocks | Maintain each players portfolio, can manage his stocks | This is Broker component.Portfolio(StockName,Quantity,PurchasePrice) | 1 | 3 | Completed
37 | Game | Player | Identify stock for each player | Unique identifier | Unique stock name for each player's stock | 2 | 3 | Completed
38 | Game | Player | Brokers account. Cannot duplicate accounts | to identify each broker. Unique identifier | CreateAccount(name). Exception handling: Account name already exit. | 2 | 3 | Completed
39 | Simulator | Player | Stock account: bank account must be created before the stock account be created. | Can do the transactions success.Broker can purchase sepecific quanity of the given stock at the given price | buy(name,stock,quantity,price). return true: Indicator success. Returns fails: Transactin Fail, Transaction fails: price does not match current market price | 2 | 3 | Completed
40 | Game | Player | The broker withdraws the specified quantity of funds from the players bank account. | Can check accounts balances for players and brokers |  | 2 | 3 | Completed
41 | Game | Player | Brokers sells the stock | Sell the specified quantity of the given stock at the given price. | sell(name,stock,quantity,price). Transaction fails: price does not match current market price and Players does not specify quantity of the stock | 2 | 3 | Completed
42 | Game | Player | The broker deposit quatity of the funds to the players account | Can check accounts balances for players and brokers |  | 2 | 3 | Completed
43 | Game | Player | Shold display current stock details for each player | get idea for each players current rates | Portfolio(name): returns current list of stocks owned by the player, quantities,purchase price. price(stock): returns the current price for each of the stocks specified in the input stocks list. | 2 | 3 | Completed
44 | Game | Player | Analyst: able to make recommendations | can select which stocks to buy and sell.can expected future price of the share.Can recommended share will be buy or sell | each turn, the Analyst has a 50% chance of gaining access to a subset of the future trends of one stock / sector.The view is limited to the next 10 turns. If the price of a share will fall by more than 10%, the analyst issues a SELL recommendation for that share. if the price of a share will increase by more than 10%, the analyst issues a BUY recommendation for that share. the number of turns needed to make that recommendation is also reported. Recommendation = time,type (stock/sector), name (stock/sector), action (buy/sell), duration. The analyst has a 60% chance of detecting an event up to 3 turns before it occurs. | 1 | 3 | Completed
45 | Simulator | Player | able to issue a BUY/SELL recommendation for that share/sector. The duration should map onto the end of the event. | Can analyst duration of each recommendation | getRecommendations() – returns a list of currently active recommendations | 1 | 3 | Completed
46 | Game | Player | should implement some strategy to play the game | Play the game | At the start of the game, it must create a bank account followed by a broker account. The player should buy and sell shares based on its strategy. play() – should be called once per turn. Results in the player applying its strategy. | 1 | 3 | Completed
47 | Game | Player | Player:Human player of the game. Player should buy/sell stock. | Can buy/sell stocks. And rates will be increase/decrease. Account balances be changed. |  | 1 | 3 | Completed
48 | Game | Player | Should automatically create players accounts. | Can entered to the game |  | 1 | 3 | Completed
49 | Game | Player | Game Board: Should show the current winner. Should display value,size in portfolio and bank balance for player wise. Should display price of all stocks. should show all events that have already occurred / are currently occurring. able to view the historical purchases / sales of each player. should show the current turn, total number of turns | Each player can find out his rates,summary of player and stocks,current turns;turns which be end, identify each player's purchase summary | Game Board component:To check historical,current views also possible | 1 | 3 | Completed

## Sprint 1 - Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
Task 1 | Task 1 | No Continued Work
Task 2 | Task 2 | No Continued Work
Task 3 | Task 3 | No Continued Work
Task 4 | Task 4 | No Continued Work
Task 5 | Task 5 | No Continued Work
Task 6 | Task 6 | No Continued Work
Task 7 | Task 7 | No Continued Work
Task 8 | Task 8 | No Continued Work
Task 9 | Task 9 | No Continued Work
Task 10 | Task 10 | No Continued Work
Task 11 | Task 11 | No Continued Work
Task 12 | Task 12 | No Continued Work
Task 13 |  | No Continued Work
Task 14 | Task 14 | No Continued Work
General Reflections
Release the Sprint 1 build

## Sprint 1
Sprint
Start date:-5/26/2018
End date:-6/2/2018
User Story | PBL ID# | Task ID# | Tasks | Estimate (hours) | Actual (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
As a Player, I want to log in to the game accessing the correct Url and give the Username | 1 | T1.1 | Research how to create a Web game | 2 | 2
|  | T1.2 | Design a solution for this game | 2 | 2
|  | T1.3 | Create Test Cases | 1 | 1
|  | T1.4 | Implement the wire frame and UI | 2 | 2
As a Player,I should able to see the option to play with multiplayer mode | 2 | T2.1 | Storyboard a UI to should display multiple players and default players | 2 | 2
|  | T2.2 | Design the logic to Users Connect and Play multiplayer mode. | 2 | 2
|  | T2.3 | Create Test Cases | 2 | 1
|  | T2.4 | Implement the logic | 3 | 2
|  | T2.5 | Implement the UI | 3 | 2
As a Player,If I log in to the game I can see the other 4 Players(either Humans or Computer). | 3 | T3.1 | Storyboard a UI to display multiple player mode with another 3 players accounts | 1 | 2
|  | T3.2 | Design the logic to play with another minimum 3 players and maximum 5 players | 2 | 2
|  | T3.3 | Create Test Cases | 2 | 2
|  | T3.4 | Implement the logic | 3 | 3
|  | T3.5 | Implement the UI | 2 | 2
As a Player, I want to see variation between the prices of shares in the market.so that share prices do not change at the same rate/have the same price. | 4 | T4.1 | Story board a UI Graphs to display the each share prices getting change with rates and time | 1 | 1
|  | T4.2 | Design the UI graphs of shares | 2 | 2
|  | T4.3 | Create Test Cases | 2 | 1
|  | T4.4 | Implement the design | 3 | 3
As a Player, I want to be able to buy shares so that I can make money | 5 | T5.1 | Storyboard a UI to capture BUY commands | 1 | 2
|  | T5.2 | Design a Service to handle the incoming request | 2 | 2
|  | T5.3 | Create Test Cases | 2 | 2
|  | T5.4 | Implement the Service | 3 | 3
|  | T5.5 | Implement the UI | 2 | 2
|  | T5.6 | Connect the Service to the UI | 2 | 1
As a Player, I want to be able to see the current price of shares so that they can decide what to buy/sell | 6 | T6.1 | Storyboard a UI to show this information | 1 | 2
|  | T6.2 | Design a Service to expose this information | 2 | 2
|  | T6.3 | Create Test Cases | 2 | 2
|  | T6.4 | Implement the Service | 3 | 2
|  | T6.5 | Implement the UI | 2 | 1
|  | T6.6 | Connect the Service to the UI | 2 | 2
As a Player, initial value should be R.S.1000 and player can buy shares if they have enough money for buy those shares. | 7 | T7.1 | Storyboard a UI to shows the initial value R.S.1000 | 1 | 2
|  | T7.2 | Design the logic to buy shares if players have enough money. | 2 | 2
|  | T7.3 | Create Test Cases | 2 | 2
|  | T7.4 | Implement the logic | 2 | 2
|  | T7.5 | Implement the UI showing the Error message or notification If player try to buy shares without Enough money | 2 | 1
|  | T7.6 | Implement the UI showing the Success message or notification If player buy shares with Enough money | 2 | 1
As a Player,able to see when bought shares the total value should be decrease From the share amount. | 8 | T8.1 | Storyboard a UI to show the balance amount | 2 | 1
|  | T8.2 | Design the logic to when bought shares the total value should be decrease From the share amount. Function *Total amount=previous amount-Shares price | 2 | 1
|  | T8.3 | Create Test Cases | 2 | 2 | [7 empty] | z
|  | T8.4 | Implement the logic | 3 | 2
|  | T8.5 | Implement the UI | 3 | 2
As a Player,I want to see my current stocks and others current stocks also can view the transaction history(record of all the stock bought/sold by the player) (The Broker Component) | 9 | T9.1 | Storyboard a UI to show the stock of all players | 2 | 2
|  | T9.2 | Design the logic to View Current stock and transaction details of all players | 3 | 2
|  | T9.3 | Create Test Cases | 2 | 1
|  | T9.4 | Implement the logic | 2 | 1
|  | T9.5 | Implement the UI | 3 | 2
As a Player, I want to sell the shares | 10 | T10.1 | Storyboard a UI to capture sell commands | 1 | 1
|  | T10.2 | Design a Service to handle the incoming request | 2 | 2
|  | T10.3 | Create Test Cases | 2 | 2
|  | T10.4 | Implement the Service | 3 | 2
|  | T10.5 | Implement the UI | 2 | 2
|  | T10.6 | Connect the Service to the UI | 2 | 2
As a Player, when I sold the shares my current balance should be increase | 11 | T11.1 | Storyboard a UI to show the balance amount | 2 | 2
|  | T11.2 | Design the logic to when sold the shares the total value should be increase Function *Total amount=previous amount+Sold share prices | 2 | 2
|  | T11.3 | Create Test Cases | 2 | 2
|  | T11.4 | Implement the Service | 3 | 3
|  | T11.5 | Implement the UI | 2 | 2
As a Player,I can Want to play the game in different Sectors and stocks. (5 Sectors and 4 stocks for each sectors) | 12 | T12.1 | Storyboard a UI to show the 5 different sectors and 4 different stocks | 2 | 0
|  | T12.2 | Design the logic for Change it different variation of the Graph for different sectors & diffrerent stocks. | 2 | 2
|  | T12.3 | Create Test Cases | 2 | 3
|  | T12.4 | Implement the Logic | 3 | 3
|  | T12.5 | Implement the UI | 2 | 2
As a Player,I want to see the BOOM,BUSTS,Take Overs,Profit warning,Scandals events in limited time BOOM Event (Prob 0.5):range +1 to +5 BUST Event (Prob 0.5 ):range -1 to -5 Profit Warning(Prob 0.5):range +2 to +3 Take Over (Prob0.25):range -1 to -5 Scandal(Prob 0.25):range -3 to -6 | 13 | T13.1 | Research about the BOOM,BUST,Take Over,scandals,Profit Warning Events | 2 | 2
|  | T13.2 | Design the logic for BOOM,BUST,Take Over,scandals,Profit Warning Events | 2 | 2
|  | T13.3 | Create Test Cases | 2 | 3
|  | T13.4 | Implement the Logic | 3 | 3
|  | T13.5 | Implement the UI | 2 | 2
As a Player, I want to play a game made up of fixed-duration turns so that I have only a limited time to decide what to buy and sell | 14 | T14.1 | Research how to create a fixed-duration turn based game | 3 | 2
|  | T14.2 | Design a solution for this game | 2 | 2
|  | T14.3 | Create Test Cases | 1 | 1
|  | T14.4 | Implement the solution | 2 | 2
|  |  | Sprint Countdown: | 149 | 134 | 25 | 10 | 30.5 | 40.5 | 14 | 7 | 7

## Sprint 2 - Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
Task 15 | Task 15 | No Continued Work
Task 16 | Task 16 | No Continued Work
Task 17 | Task 17 | No Continued Work
Task 18 | Task 18 | No Continued Work
Task 19 | Task 19 | No Continued Work
Task 20 | Task 20 | No Continued Work
Task 21 | Task 21 | No Continued Work
Task 22 | Task 22 | No Continued Work
Task 23 | Task 23 | No Continued Work
Task 24 | Task 24 | No Continued Work
Task 25 | Task 25 | No Continued Work
Task 26 | Task 26 | No Continued Work
Task 27 | Task 27 | No Continued Work
General Reflections
Release the Sprint 1 build

## Sprint 2
Sprint
Start date:-6/3/2018
End date:-6/10/2018
User Story | PBL ID# | Task ID# | Tasks | Estimate (hours) | Actual (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
As a Player, I want to play a game should be modelled as a discrete time system. | 15 | T15.1 | Research on how to model a game as a discrete time system | 1 | 1
|  | T15.2 | Design a solution for this game | 1 | 1
|  | T15.3 | Create Test Cases | 1 | 1
|  | T20.4 | Implement the solution | 2 | 2
As a Player, I should be able to use my turn to buy shares | 16 | T16.1 | Storyboard a UI to display 10 turns to buy shares | 1 | 1
|  | T16.2 | Design the logic to play by buying shares. | 1 | 1
|  | T16.3 | Create Test Cases | 2 | 1
|  | T16.4 | Implement the logic | 2 | 2
|  | T16.5 | Implement the UI | 2 | 2
As a Player, I should be able to use my turn to sell shares. | 17 | T17.1 | Storyboard a UI to display 10 turns to sell shares | 1 | 1
|  | T17.2 | Design the logic to play by selling shares | 2 | 2
|  | T17.3 | Create Test Cases | 2 | 2
|  | T17.4 | Implement the logic | 2 | 2
|  | T17.5 | Implement the UI | 2 | 2
As a Player,when I entered the game, I should be able to buy shares within 10 minutes of time. | 18 | T18.1 | Storyboard a UI to display the constant time for buying shares. | 2 | 2
|  | T18.2 | Design the UI with time features | 2 | 2
|  | T18.3 | Create Test Cases | 2 | 2
|  | T18.4 | Implement the clock design | 2 | 2
|  | T18.5 | Implement the UI | 2 | 2
As a Player, when I entered the game, I should be able to sell shares within 10 minutes of time. | 19 | T19.1 | Story board a UI to display the constant time for selling shares. | 1 | 1
|  | T19.2 | Design the UI with time features | 2 | 2
|  | T19.3 | Create Test Cases | 2 | 1
|  | T19.4 | Implement the clock design | 2 | 2
|  | T19.5 | Implement the UI | 2 | 2
As a Player, I want to be able to see the share price goes up after buying/selling the shares. | 20 | T20.1 | Storyboard a UI to show the random changing share price. | 1 | 3
|  | T20.2 | Design the UI graph of share price | 2 | 2
|  | T20.3 | Create Test Cases | 2 | 1
|  | T20.4 | Implement the graph design | 3 | 3
|  | T20.5 | Implement the UI | 2 | 2
|  |  |  | 2 | 2
As a Player, I want to be able to see the share price goes down after buying/selling the shares. | 21 | T21.1 | Storyboard a UI to show the random changing share price. | 1 | 2
|  | T21.2 | Design the UI graph of share price | 2 | 2
|  | T21.3 | Create Test Cases | 2 | 1
|  | T21.4 | Implement the graph design | 3 | 3
|  | T21.5 | Implement the UI | 2 | 2
As a Player, I should be able to buy shares at any time. | 22 | T22.1 | Storyboard a UI to show the available shares to buy | 1 | 1
|  | T22.2 | Design the logic to buy shares if players have enough money. | 2 | 2
|  | T22.3 | Create Test Cases | 1 | 1
|  | T22.4 | Implement the logic | 2 | 2
|  | T22.5 | Implement the UI | 2 | 2
A a Player, I should be able to sell shares at any time. | 23 | T23.1 | Storyboard a UI to show the shares other players wanted to buy | 2 | 2
|  | T23.2 | Design the logic to buy shares if players have enough money. | 3 | 3
|  | T23.3 | Create Test Cases | 1 | 1
|  | T23.4 | Implement the logic | 2 | 2
|  | T23.5 | Implement the UI | 3 | 3
As a Player, I should have stock market model, which includes Value Change Algorithm | 24 | T24.1 | Research on how to model a game with value changing algorithm. | 2 | 2
|  | T24.2 | Design a solution for this scenario. | 2 | 3
|  | T24.3 | Create Test Cases | 1 | 1
|  | T24.4 | Implement the solution | 3 | 4
As a Player, I want to be able to see each component of the algorithm combines to give an overall percentage change in the value of share. | 25 | T25.1 | Research on how to model a game with percentage change in the value of share | 2 | 2
|  | T25.2 | Design a solution for this scenario. | 2 | 2
|  | T25.3 | Create Test Cases | 1 | 1
|  | T25.4 | Implement the solution | 3 | 4
As a Player, I want to be able to see the Random Market Component (Stocks change amount between -2 and +2). | 26 | T26.1 | Storyboard a UI to show the random market component values | 2 | 2
|  | T26.2 | Design the UI graph of share changes | 2 | 2
|  | T26.3 | Create Test Cases | 1 | 1
|  | T26.4 | Implement the graph design | 3 | 3
|  | T26.5 | Implement the UI | 2 | 2
As a Player, I want to be able to see the Sector Trend Market Component (Stocks in a specified sector change by an amount between -3 and +3). | 27 | T27.1 | Storyboard a UI to show the sector trend market component values | 2 | 2
|  | T27.2 | Design the UI graph of share changes | 2 | 2
|  | T27.3 | Create Test Cases | 1 | 2
|  | T27.4 | Implement the graph design | 3 | 4
|  | T27.5 | Implement the UI | 2 | 2
|  |  | Sprint Countdown: | 118 | 122 | 17 | 15 | 23 | 21 | 27 | 15 | 5

## Sprint 3 - Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
Task 28 | Task 28 | No Continued Work
Task 29 | Task 29 | No Continued Work
Task 30 | Task 30 | No Continued Work
Task 31 | Task 31 | No Continued Work
Task 32 | Task 32 | No Continued Work
Task 33 | Task 33 | No Continued Work
Task 34 | Task 34 | No Continued Work
Task 35 | Task 35 | No Continued Work
Task 36 | Task 36 | No Continued Work
Task 37 | Task 37 | No Continued Work
Task 38 | Task 38 | No Continued Work
General Reflections
Release the Sprint 3 build

## Sprint 3
Sprint
Start date:-6/11/2018
End date:-6/18/2018
User Story | PBL ID# | Task ID# | Tasks | Estimate (hours) | Actual (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
As a Player, I want to be able to see the General Trend Market Component (All stocks in the market change by an amount between -3 and +3) | 28 | T28.1 | Storyboard a UI to show the general trend market component values | 1 | 1
|  | T28.2 | Design the UI graph of share changes | 1 | 1
|  | T28.3 | Create Test Cases | 1 | 1
|  | T28.4 | Implement the graph design | 2 | 2
|  | T28.5 | Implement the UI | 1 | 2
As a Player, I want to be able to see the Event Component (Calculated as the sum of the scores of all relevant events active at the given time point.) | 29 | T29.1 | Storyboard a UI to show the event component values | 1 | 1
|  | T29.2 | Design the UI graph of share changes | 2 | 2
|  | T29.3 | Create Test Cases | 2 | 2
|  | T29.4 | Implement the graph design | 2 | 2
|  | T29.5 | Implement the UI | 1 | 1
As a Player, I should be able to see negative scores are interpreted as 0, normally at the start of each turn | 30 | T30.1 | Storyboard a UI to show negative score as 0 normally at the start of each turn | 2 | 2
|  | T30.2 | Design a solution for this scenario. | 2 | 2
|  | T30.3 | Create Test Cases | 2 | 2
|  | T30.4 | Implement the solution | 2 | 2
|  | T30.5 | Implement the UI | 2 | 2
As a Player, for each turn I should see probabilities in value changes P(Value Increases) = 0.25 P(Value Decreases) = 0.25 P(Value Does Not Change) = 0.5 | 31 | T31.1 | Storyboard a UI to show value change probabilities | 2 | 2
|  | T31.2 | Design the UI graph of value changes | 2 | 2
|  | T31.3 | Create Test Cases | 2 | 2
|  | T31.4 | Implement the graph design | 1 | 2
|  | T31.5 | Implement the UI | 2 | 1
As a Player, I should see unique trend is created for each sector | 32 | T32.1 | Storyboard a UI to show unique trend in each sector | 2 | 2
|  | T32.2 | Design the logic to uniquely identify trends | 2 | 2
|  | T32.3 | Create Test Cases | 1 | 1
|  | T32.4 | Implement the logic | 2 | 2
|  | T32.5 | Implement the UI | 2 | 2
I
As a Player, I want to be able to see one event should be generated per turn. | 33 | T33.1 | Storyboard a UI to generated one event per turn | 1 | 1
|  | T33.2 | Design the logic | 2 | 3
|  | T33.3 | Create Test Cases | 1 | 1
|  | T33.4 | Implement the logic | 2 | 2
|  | T33.5 | Implement the UI | 2 | 2
As a Player, I want to be able to see probability increases by 0.1 | 34 | T34.1 | Storyboard a UI to generated one event per turn | 2 | 2
|  | T34.2 | Design the logic | 2 | 2
|  | T34.3 | Create Test Cases | 1 | 1
|  | T34.4 | Implement the logic | 2 | 2
|  | T34.5 | Implement the UI | 2 | 2
As a Player, I want to display current turn of the game | 35 | T35.1 | Research how to create a current-turn based game | 2 | 2
|  | T35.2 | Design logic for the turn | 2 | 3
|  | T35.3 | Create Test cases | 1 | 1
|  | T35.4 | Implement solution. (UI: CLOCK) | 2 | 3
As a Player, I want to do the transactions through the bank | 36 | T36.1 | Storyboard a UI to should display the deposit,withdrawal and transactions details. | 2 | 2
|  | T36.2 | Design the logic to select deposit mode or withdrawal mode. | 2 | 1
|  | T36.3 | Create Test Cases | 2 | 2
|  | T36.4 | Implement the logic | 3 | 3
|  | T36.5 | Implement the UI | 3 | 3
As a Player, want to bank account ,and need to identify uniquely | 37 | T37.1 | Storyboard a UI to shold display bank accounts for players ans shows the initial value R.S.1000 | 1 | 1
|  | T37.2 | Design the logic to create account uniquely. | 2 | 2
|  | T37.3 | Create Test Cases | 2 | 2
|  | T37.4 | Implement the logic | 2 | 4
|  | T37.5 | Implement the UI showing the Error message or notification when create duplicate accounts | 2 | 2
|  | T37.6 | Implement the UI showing the Success message or notification when create unique account | 2 | 2
As a Player, I want to be able to buy/sell stocks so that I can mainain portfolio and manage stocks | 38 | T38.1 | Storyboard a UI to capture BUY/SELL commands | 1 | 1
|  | T38.2 | Design a Service to handle the incoming/outgoing request | 2 | 3
|  | T38.3 | Create Test Cases | 2 | 2
|  | T38.4 | Implement the Service | 3 | 5
|  | T38.5 | Implement the UI | 2 | 3
|  | T38.6 | Connect the Service to the UI | 2 | 3
|  |  | Sprint Countdown: | 101 | 111 | 12.5 | 17 | 32.5 | 32.2 | 5.6 | 5.6 | 5.6

## Sprint 4 - Review
Sprint Reflections
Review what worked/did not work/should be done…
Start | Stop | Continue
Task 39 | Task 39 | No Continued Work
Task 40 | Task 40 | No Continued Work
Task 41 | Task 41 | No Continued Work
Task 42 | Task 42 | No Continued Work
Task 43 | Task 43 | No Continued Work
Task 44 | Task 44 | No Continued Work
Task 45 | Task 45 | No Continued Work
Task 46 | Task 46 | No Continued Work
Task 47 | Task 47 | No Continued Work
Task 48 | Task 48 | No Continued Work
Task 49 | Task 49 | No Continued Work
General Reflections
Release the Sprint 4 build

## Sprint 4
Sprint
Start date:-6/18/2018
End date:-6/25/2018
User Story | PBL ID# | Task ID# | Tasks | Estimate (hours) | Actual (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
As a Player, I need to identify stock for each player uniquely | 39 | T39.1 | Storyboard a UI to shold display stock for players | 1 | 1
|  | T39.2 | Design the logic to create stock uniquely. | 2 | 2
|  | T39.3 | Create Test Cases | 2 | 2
|  | T39.4 | Implement the logic | 3 | 3
|  | T39.5 | Implement the UI | 2 | 3
As a Broker, want to account ,and need to identify uniquely | 40 | T40.1 | Storyboard a UI to shold display Brokers accounts | 1 | 1
|  | T40.2 | Design the logic to create account uniquely. | 2 | 2
|  | T40.3 | Create Test Cases | 1 | 1
|  | T40.4 | Implement the logic | 2 | 4
|  | T40.5 | Implement the UI showing the Error message or notification when create duplicate accounts | 2 | 3
|  | T40.6 | Implement the UI showing the Success message or notification when create unique account | 2 | 3
As a want to crete stock account so Broker can purchase the stocks | 41 | T41.1 | Storyboard a UI to capture BUY commands | 1 | 1
|  | T41.2 | Design the logic to buy stock . | 2 | 2
|  | T41.3 | Create Test Cases | 2 | 2
|  | T41.4 | Implement the logic | 2 | 3
|  | T41.5 | Implement the UI showing the Error message or notification if price does not matchcurrent market price | 2 | 2
|  | T41.6 | Implement the UI showing the Success message or notification when buy the stocks | 2 | 2
As a broker want to withdraws the specified quantity of funds from the players bank account. | 42 | T42.1 | Storyboard a UI to capture WITHDRAWAL commands | 1 | 1
|  | T42.2 | Design the logic to withdrawal . | 2 | 2
|  | T42.3 | Create Test Cases | 2 | 1
|  | T42.4 | Implement the logic | 2 | 3
|  | T42.5 | Implement the UI | 2 | 3
As a Broker, I want to be able to sell stocks. | 43 | T43.1 | Storyboard a UI to capture SELL commands | 1 | 1
|  | T43.2 | Design the logic to sell the stock . | 2 | 2
|  | T43.3 | Create Test Cases | 2 | 2
|  | T43.4 | Implement the logic | 2 | 2
|  | T43.5 | Implement the UI showing the Error message or notification if price does not matchcurrent market price and does not enter quantity of the stock | 2 | 3
|  | T43.6 | Implement the UI showing the Success message or notification when buy the stocks | 2 | 3
As a broker want to deposit the specified quantity of funds from the players bank account. | 44 | T44.1 | Storyboard a UI to capture DEPOSIT commands | 1 | 1
|  | T44.2 | Design the logic to deposit. | 2 | 2
|  | T44.3 | Create Test Cases | 2 | 2
|  | T44.4 | Implement the logic | 2 | 2
|  | T44.5 | Implement the UI | 2 | 2
As a Player,when I entered the game I able to see the following features in current stock details for each player *current list of stocks owned by the player *quantities. *purchase price | 45 | T45.1 | Storyboard a UI to should display the stock details | 1 | 1
|  | T45.2 | Design the UI with following features | 2 | 2
|  | T45.3 | Create Test Cases | 2 | 2
|  | T45.4 | Implement the design | 2 | 2
|  | T45.5 | Implement the UI | 2 | 2
As a Player, I want to be able to make recommendation so that I can recommended be buy or sell | 46 | T46.1 | Storyboard a UI to capture recommendation commands | 1 | 1
|  | T46.2 | Design a logic Service to handle the request | 2 | 3
|  | T46.3 | Design Service to handle the recommendation | 2 | 4
|  | T46.4 | Create Test Cases | 2 | 1
|  | T46.5 | Implement the Service | 2 | 3
|  | T46.6 | Implement the UI | 2 | 2
|  | T46.7 | Connect the Service to the UI | 2 | 3
As a Player able to recommendation duration should map onto the end of the event. So that I can analyst duration of each recomandation | 47 | T47.1 | Storyboard a UI to shold display recommendation commands | 1 | 1
|  | T47.2 | Design the logic to get recommendation. | 2 | 2
|  | T47.3 | Create Test Cases | 2 | 1
|  | T47.4 | Implement the logic | 2
|  | T47.5 | Implement the UI | 2 | 3
As a Player I want to make should some strategy to play the game | 48 | T48.1 | Storyboard a UI to should display the strategy of the game. | 1 | 1
|  | T48.2 | Design the logic to strategy. | 2 | 2
|  | T48.3 | Create Test Cases | 2 | 2
|  | T48.4 | Implement the logic | 2 | 2
|  | T48.5 | Implement the UI | 2 | 3
As a Player,when I entered the game I able to see the following features in Game Board *current winner. *value,size in portfolio and bank balance for player wise *price of all stocks. * all events that have already occurred / are currently occurring. *the historical purchases / sales of each player. *the current turn, total number of turns *Historical records and Current values of share prices | 49 | T49.1 | Storyboard a UI to should display the stock details | 1 | 1
|  | T49.2 | Design the UI with following features | 2 | 2
|  | T49.3 | Create Test Cases | 2 | 1
|  | T49.4 | Implement the design | 2 | 3
|  | T49.5 | Implement the UI | 2 | 3
|  |  | Sprint Countdown: | 109 | 122 | 25 | 10 | 10 | 19.5 | 30.5 | 13.5 | 13.5